## 1 · Summary
Quantum Force 9000 — DPU Acceleration Card
What it takes to deliver the solution · dynamic investment, risk & delivery model (expanded from Slide 15)
Metric | Value | Basis / source | Assumption
Objective | TP+TLS: 10.1G → 25G+ | CP Appliance Comparison Chart 2026 | Lift Threat-Prevention throughput with TLS inspection on; PoC success gate
Approach | Reuse NVIDIA BlueField-3 (DOCA) | Check Point AI Cloud Protect (AIFF) press release | Not an own ASIC and not a self-designed FPGA — fastest, lowest-risk path
Expected throughput multiple | ≈ 4× (10 → ~40G) | NVIDIA BlueField-3 datasheet | Ceiling then set by x86 policy processing
Loaded cost / engineer |  | Internal planning estimate | Default rate; individual roles can differ (Investment · drill-down B)
Total investment (NRE) |  | Internal planning estimate | Live link to the Investment total — changes with the inputs
R&D team (FTE) |  | Internal planning estimate | Fully-loaded; most sit on the offload boundary
Duration to GA (months) |  | Internal planning estimate | Effort estimate, not a schedule commitment
Top risk | Offload boundary (TP gain) | Internal planning estimate | Mitigated by a TLS-focused PoC gate before full commitment
Investment at a glance (live from the Investment sheet)
Workstream | Amount (USD) | % of total | Basis / source
R&D · engineers × duration |  |  | Internal planning estimate
HW engineering · thermal · FIPS |  |  | CP Appliance Comparison Chart 2026
Dev kits · NVIDIA NRE |  |  | NVIDIA BlueField-3 datasheet
GTM · launch |  |  | Internal planning estimate
Total
Throughput logic — which numbers are datasheet vs. estimate
9800 published (CP Appliance Chart 2026): 400G raw · 67.7G NGFW · 25G TP · 10.1G TP+TLS. Only the final ~40G is an estimate — everything else is a datasheet number, and the multiples are just division.
Step | TP+TLS | Datasheet / estimate | How we get the number
Today — on the x86 | 10.1G | Datasheet | 9800 "TP with HTTPS inspection" (published)
The TLS tax | 25G → 10.1G | Datasheet | TLS decrypt + inspect + re-encrypt on the x86 costs about 2.5x (25 / 10.1 = 2.48x)
Offload TLS → BF-3 | ~25G | Anchored to datasheet | Removes the TLS tax -> back to the 25G plain-TP ceiling
Offload IPS (RXP) → BF-3 | ~40G | Estimate (only soft number) | Climbs above 25G TP toward the 67.7G NGFW number; ~40G, limited by x86 policy
Expected multiple | ≈ 4× | Derived | 40 / 10.1 = 3.96x ~ 4x
PoC Go / No-Go gate | 25G+ (2.5×) | Conservative target | 25 / 10.1 = 2.48x - just recover the TLS tax
Bottom line: 10.1G and 25G are the 9800’s own datasheet numbers; offloading TLS just returns you to 25G. Offloading IPS is the estimated step that adds the rest to ~40G — bounded above by the 67.7G NGFW figure and limited by x86 policy. The PoC validates that single soft number.
Check Point Software Technologies · Confidential ¦ Barak Rozenfeld · Senior PM Assignment 2026 ¦ Slide 15 ¦ Cream = editable input · grey = formula (recalculates).

## 2 · Investment
Investment — dynamic cost model with drill-down
Edit the cream cells (salary, overhead, quantities, unit costs, and the per-role engineer rates). Grey cells are formulas; totals roll up automatically. Each line shows its basis/source and assumption.
Cost summary · rolls up from the drill-down blocks below
Category | Amount (USD) | % of total |  | Basis / source | Assumption
R&D (engineers × role rate × years) |  |  |  | Internal planning estimate | Rolls up from the per-role build-up (drill-down B)
Hardware engineering · thermal · FIPS |  |  |  | CP Appliance Comparison Chart 2026 | Mechanical/thermal, PSU validation, FIPS lab
Dev kits / NRE |  |  |  | NVIDIA BlueField-3 datasheet | BF-3 boards, DOCA, NVIDIA NRE, lab/test
GTM / launch |  |  |  | Internal planning estimate | Beta, launch, enablement, PoC support
Total
Hardware eng. | Card bring-up · thermal · FIPS lab | CP Appliance Comparison Chart 2026 | Mechanical/thermal design, PSU validation, FIPS 140-3 test lab
Drill-down A · R&D engineer cost build-up
Driver | Value | Unit |  | Basis / source | Assumption
Base salary | 170000 | $ / year |  | Internal planning estimate | Blended senior-engineer base salary
Overhead multiplier | 40% | × of salary |  | Internal planning estimate | Benefits, facilities, management, G&A
Tooling & licenses | 12000 | $ / eng / yr |  | Internal planning estimate | Dev tools, cloud, lab share per engineer
Default loaded cost / engineer |  | $ / year |  | Internal planning estimate | Default rate; each role in drill-down B defaults to this and can be tuned by seniority
Engineers (FTE) | 12 | FTE |  | Internal planning estimate | Most sit on the CoreXL↔card offload boundary
Duration | 18 | months |  | Internal planning estimate | Effort estimate to GA, not a schedule commitment
Duration (years) = months ÷ 12 |  | years |  | Internal planning estimate | Forward factor used by the role table: cost = engineers × rate/yr × years
Validation / performance | PoC, automation, perf & regression | Internal planning estimate | Measures the real gain before full commitment | 2
Drill-down B · R&D headcount by role (engineers should sum to the FTE above)
Role | Engineers | Loaded $/yr · per person | Cost (USD) | Basis / source | Assumption
DOCA bring-up / Gaia driver | 3 | 260000 |  | Check Point AI Cloud Protect (AIFF) press release | Driver/kernel specialists — rate above blended
Offload API / CoreXL (the core) | 5 | 260000 |  | Internal planning estimate | Senior core engineers — where most of the risk sits
Signature compiler (RXP) | 2 | 250000 |  | NVIDIA BlueField-3 datasheet | RXP / compiler specialists — blended rate
Validation / performance | 2 | 210000 |  | Internal planning estimate | QA / performance mix — below blended
Subtotal R&D · flows to the Cost summary (R&D row)
Drill-down C · Hardware engineering
Item | Qty | Unit cost | Cost (USD) | Basis / source | Assumption
Mechanical & thermal design | 1 | 500000 |  | Internal planning estimate | 1RU airflow, chassis & card mechanics
PSU / signal-integrity validation | 1 | 300000 |  | CP Appliance Comparison Chart 2026 | Electrical headroom for ~75W added
FIPS 140-3 lab & certification | 1 | 400000 |  | NIST CMVP (FIPS 140-3) | BF-3 crypto module already approved
Subtotal |  |  |  | → feeds the Cost summary
Drill-down D · Dev kits / NRE
Item | Qty | Unit cost | Cost (USD) | Basis / source | Assumption
BF-3 development boards | 10 | 15000 |  | NVIDIA BlueField-3 datasheet | Dev/test units for the engineering team
DOCA SDK / support | 1 | 120000 |  | NVIDIA BlueField-3 datasheet | SDK, licenses and developer support
NVIDIA NRE / integration | 1 | 400000 |  | NVIDIA BlueField-3 datasheet | Non-recurring engineering with NVIDIA
Lab / test equipment | 1 | 130000 |  | Internal planning estimate | Traffic generators, TLS test harness
Subtotal |  |  |  | → feeds the Cost summary
Drill-down E · GTM / launch
Item | Qty | Unit cost | Cost (USD) | Basis / source | Assumption
Beta / design-partner program | 1 | 300000 |  | Internal planning estimate | Design partners before GA
Launch & collateral | 1 | 200000 |  | Internal planning estimate | Positioning, datasheets, web
Sales enablement & PoC support | 1 | 200000 |  | Internal planning estimate | Enablement + PoC engineering support
Subtotal |  |  |  | → feeds the Cost summary
How to play with it: change any cream cell (Base salary, Overhead, Engineers, a per-role $/yr rate, a Qty or a Unit cost) — the grey Cost/Amount/% cells, the subtotals and the grand Total all recalculate, and the Summary sheet follows.
Check Point Software Technologies · Confidential ¦ Barak Rozenfeld · Senior PM Assignment 2026 ¦ Slide 15 ¦ Cream = editable input · grey = formula (recalculates).
Phase split — what the $2.9M PoC covers vs the $4.3M to GA
PoC = first ~6 months · success gate 25 Gbps+ under TLS · if the gate is missed, we stop before the $4.3M GA spend. The split is a phase allocation of the same $7.2M program above.
Category | Total (USD) | PoC phase (≤6 mo) | GA phase (≤12 mo) | Basis / what is spent in the PoC
R&D (engineers × rate × time) |  |  |  | PoC runs a subset of the team — 10 eng × 6 mo (see build-up below)
Hardware eng · thermal · FIPS |  | 600000 |  | Early thermal/mech work + FIPS 140-3 scoping during the PoC
Dev kits / NRE |  | 650000 |  | BF-3 boards + DOCA + NVIDIA NRE + lab bought up-front for the PoC
GTM / launch |  | 400000 |  | Design-partner prep + PoC engineering support
Total |  |  |  | PoC ≈ $2.9M · GA ≈ $4.3M · total $7.2M
PoC R&D build-up · drives the R&D PoC cell above
Driver | Value | Unit |  | Note
Engineers (PoC) | 10 | FTE |  | Focused subset — core offload + driver + perf
Duration (PoC) | 6 | months |  | To the 25 Gbps+ gate
Loaded cost / engineer-month |  | $ / mo
PoC R&D = engineers × months × rate |  | USD |  | ≈ $1.25M — flows up to the R&D PoC cell

## 3 · Timeline
Delivery timeline — 18-month effort (with PoC gate)
Effort allocation (person-/calendar-months), not a committed schedule; phases overlap. The Proof of Concept is an integral Go/No-Go gate.
Phase | Focus | Effort (mo) | Window | Key deliverables | Exit criterion / milestone | Basis / source | Assumption
DOCA bring-up | Gaia driver + DOCA SDK on BF-3 (based on the AIFF gateway) | 3 | M0 – M3 | Driver loads; zero-copy DMA path | Traffic passes through the card | Check Point AI Cloud Protect (AIFF) press release | Reuse the AIFF containerized gateway already on BF-3
Offload API (the core) | CoreXL ↔ card API; TLS decrypt/re-encrypt + IPS offload | 5 | M3 – M8 | TLS offloaded to the DPU engines | Offload path functional end-to-end | Internal planning estimate | Most of the engineers; the core technical work
Proof of Concept · TLS gate | Measure the real TP+TLS gain on a 9800 + BF-3 before full commitment | 2 | M8 – M10 | Benchmarked 9800 + card under TLS inspection | Go / No-Go gate: 25G+ TP under TLS | CP Appliance Comparison Chart 2026 | De-risks the offload-boundary assumption before RXP/FIPS spend
RXP + FIPS | IPS DB → RXP signature compiler; FIPS 140-3 filed early | 4 | M10 – M14 | ~85% of signatures compiled; FIPS filed | Hybrid IPS gain measured; FIPS in review | NIST CMVP (FIPS 140-3) | FIPS filed ~9 mo before GA; BF-3 crypto module approved
Beta → GA | Design-partner beta, hardening, launch | 4 | M14 – M18 | Beta with design partners; GTM ready | General Availability (GA) | Internal planning estimate | Design-partner program before GA
Total effort
Note: effort months sum to 18; calendar windows overlap. FIPS 140-3 is submitted ≈ 9 months before GA (not after).
Note: effort months sum to 18; calendar windows overlap. The PoC (M8–M10) is a Go/No-Go gate — the project only commits to RXP/FIPS spend after 25G+ under TLS is demonstrated. FIPS 140-3 is submitted ≈ 9 months before GA.
Check Point Software Technologies · Confidential ¦ Barak Rozenfeld · Senior PM Assignment 2026 ¦ Session 1 · Slide 15 — What it takes to deliver the solution ¦ Edit the yellow input cells; grey cells are formulas.
Check Point Software Technologies · Confidential ¦ Barak Rozenfeld · Senior PM Assignment 2026 ¦ Slide 15 ¦ Cream = editable input · grey = formula (recalculates).

## 4 · Requirements
Requirements to deliver
Hardware, software/integration and product readiness — each with a target metric, its basis/source and the assumption to validate.
Domain | Requirement | Detail | Target metric | Basis / source | Assumption / to validate
Hardware | Form factor | Acceleration card in one of the two network I/O slots of the 9700/9800 | 1 of 2 I/O slots | Quantum Force 9800 datasheet | Check Point card model, not a generic PCIe x16 slot
| Power & thermal | ~75W extra; verify PSU headroom and airflow in 1RU | ≤ ~75W added | CP Appliance Comparison Chart 2026 | Early thermal sim; if no headroom → factory option next gen
| Data path | Zero-copy DMA without degrading the firewall-path latency | 1.85µs FW path preserved | CP Appliance Comparison Chart 2026 | DMA integration validated in PoC
Software & integration | Gaia driver + DOCA SDK | Based on the AIFF containerized gateway, already on BF-3 | Reuse AIFF stack | Check Point AI Cloud Protect (AIFF) press release | Vendor relationship & platform already in production
| Offload boundary | The API between CoreXL and the card — most of the 12 engineers | TP ≥ 25G under TLS | Internal planning estimate | Core technical risk; measured in the PoC
| Signature compiler | Converting the IPS DB → RXP; metric is % of signatures that compile | ~85% signatures compile | NVIDIA BlueField-3 datasheet | Partial IPS acceptable — TLS offload delivers most of the gain
Product readiness | Certification | Maintain FIPS 140-3; assess the card’s impact on CC certification | FIPS filed ~9 mo pre-GA | NIST CMVP (FIPS 140-3) | BF-3 already has an approved crypto module; submit early
| Customer experience | No change to SmartConsole or to the existing security policy | Zero policy change | Internal planning estimate | Transparent to existing deployments
| Launch | Beta with design partners before GA | Beta → GA | Internal planning estimate | Design-partner program defined
Check Point Software Technologies · Confidential ¦ Barak Rozenfeld · Senior PM Assignment 2026 ¦ Session 1 · Slide 15 — What it takes to deliver the solution ¦ Edit the yellow input cells; grey cells are formulas.

## 5 · Risk register
Risk register
Severity × Likelihood (High=3, Medium=2, Low=1; Score = S×L). Each risk carries its basis/source, mitigation and a measurable target.
# | Risk | Description | Severity | Likelihood | Score | Mitigation | Measurable target (KPI) | Basis / source | Owner
1 | Offload boundary | Threat-Prevention throughput does not rise as expected once offloaded | High | Medium | 6 | A TLS-focused PoC gate that measures the real gain before full commitment | 25G+ under TLS | Internal planning estimate | R&D
2 | Signature coverage on RXP | Only part of the IPS signatures compile to RXP → partial IPS gain | Medium | Medium | 4 | Not dependent on IPS: TLS offload alone delivers most of the gain (hybrid) | ~85% signatures | NVIDIA BlueField-3 datasheet | R&D
3 | Power / thermal in 1RU | No electrical / airflow headroom for the card in the 1RU box | Medium | Low | 2 | Early thermal simulation; if no headroom → factory option next generation | ~75W added | CP Appliance Comparison Chart 2026 | HW engineering
4 | Dependence on NVIDIA | Single vendor in the data path | Medium | Low | 2 | Multi-year AIFF agreement + abstraction layer to switch vendors in gen 2 | 2 vendor options | Check Point AI Cloud Protect (AIFF) press release | Product / Procurement
5 | FIPS / CC re-certification | Re-certification risk for regulated customers | Low | Low | 1 | Early FIPS submission (not after GA); BF-3 already has an approved crypto module | ~9 mo before GA | NIST CMVP (FIPS 140-3) | Compliance
Legend — Severity/Likelihood: High (3) · Medium (2) · Low (1). Score 6 = red, 3–4 = amber, 1–2 = green. Risk severity ranking is a qualitative assessment.
Check Point Software Technologies · Confidential ¦ Barak Rozenfeld · Senior PM Assignment 2026 ¦ Slide 15 ¦ Cream = editable input · grey = formula (recalculates).

## 6 · ROI
ROI — 3-year business case (expanded from Slide 16)
Why the numbers, how they are built, and the sales assumptions (incl. 29100/29200 cannibalization). Cream = editable input · grey = formula. The one-time investment links live to the Investment sheet.
Headline — 3-year outcome (base vs. base + deal upside)
Metric | Base | Base + upside |  | Basis / source | Assumption
3-year revenue |  |  |  | Build-ups A & B + upside deals | Module revenue, plus DC/HQ deal revenue in the upside
Gross profit |  |  |  | Margins applied per line | 65% on modules, 60% on DC/HQ deals
Net contribution (3 yr) |  |  |  | Gross profit − cannibalization − investment | One-time investment is a planning estimate
ROI (3 yr) |  |  |  | Net ÷ investment | Net ÷ investment, net of cannibalization; deck shows ~189% / ~408% (sheet exact)
Break-even (months from GA) | 16 | — |  | Modules only | Demand concentrated in year 1
Key inputs — editable (cream); each with its basis and assumption
Driver | Value | Unit |  | Basis / source | Assumption
Module price (ASP uplift) | 15000 | $ / module |  | IDC + Check Point IR, planning | List before channel discount; the uplift added to a deal
Annual 9700/9800 shipments | 1500 | units / yr |  | IDC Security Appliance Tracker | New-unit base the module attaches to
Attach rate — year 1 | 30% | % |  | Planning | Ramp start, first year after GA
Attach rate — year 2 | 40% | % |  | Planning | Mid ramp
Attach rate — year 3 | 50% | % |  | Planning | Mature attach rate
Installed-base upgrades (3 yr) | 925 | modules |  | Planning | Share of the installed base upgrading; demand concentrated in year 1
Gross margin — module | 65% | % |  | Check Point product standard | Blended software + hardware module margin
Gross margin — DC/HQ deal | 60% | % |  | Check Point deal standard | Hardware-heavy deal margin
One-time investment |  | $ |  | Live link → '2 · Investment'!B9 | Planning estimate: R&D, HW+FIPS, dev kits, GTM
Horizon | 3 | years |  | Standard business case | 3-year planning horizon
DC/HQ deals won / yr (upside) | 25 | deals / yr |  | Planning (+10 pts win-rate) | Incremental wins from the 4× TP+TLS advantage
DC/HQ deal value (upside) | 350000 | $ / deal |  | Planning | Average DC/HQ deal ASP
Build-up A — attach on new units (how 1,800 modules & $27.0M arise)
Year | New units | Attach % | Modules | Revenue | Assumption
Year 1 |  |  |  |  | Ramp start
Year 2 |  |  |  |  | Mid ramp
Year 3 |  |  |  |  | Mature attach
Subtotal |  |  |  |  | 1,800 modules over 3 years as attach grows 30% → 50%
Build-up B — base module revenue (3 years)
Component |  | Modules | Revenue | Basis / source | Assumption
Attach on new units |  |  |  | Build-up A | New-unit attach, years 1–3
Installed-base upgrades |  |  |  | Planning | 925 upgrades × $15K; demand concentrated in year 1
Total module revenue |  |  |  |  | Flows into the ROI waterfall as base revenue
ROI waterfall — base vs. base + deal upside
Line | Base | Base + upside |  | Basis / source | Assumption
Module revenue (3 yr) |  |  |  | Build-up B | Same in both scenarios
DC/HQ deal revenue (upside) | 0 |  |  | Upside only | 75 deals (25/yr × 3) × $350K
Total revenue |  |  |  |  | Module + upside deals
Gross profit |  |  |  | Margins per line | 65% module · 60% deal
One-time investment |  |  |  | Investment sheet | Planning estimate
Net contribution (3 yr) |  |  |  |  | Gross profit − investment
ROI (3 yr) |  |  |  | Net ÷ investment | Net of cannibalization; deck shows ~189% base / ~408% upside
Break-even (months from GA) | 16 | — |  | Modules only | Cash contribution covers the investment by ~month 16
Sales adjustment — 29100/29200 cannibalization (now netted into the headline ROI)
Why a decline in 29100/29200 sales: the module lets a stuck 9700/9800 customer gain TP+TLS without the 2RU/4RU forklift to a 29100/29200, so a share of would-be 29100/29200 buyers upgrade the existing box instead. This net impact is now BAKED INTO the headline Net contribution and ROI above (to match the deck); the pre-cannibalization figures are kept below as a memo. Most stuck customers avoid the forklift, so the displaced share is modest. All figures are planning assumptions to validate against CRM / pricing data.
Line | Value | Unit |  | Basis / source | Assumption
Cannibalization rate | 10% | % of upgrades |  | Planning estimate | Share of the 925 upgrades that would otherwise have bought a 29100/29200
29100/29200 ASP | 120000 | $ / unit |  | Planning estimate (validate w/ pricing) | Enterprise appliance; varies by bundle/region/discount — placeholder to edit
29100/29200 gross margin | 60% | % |  | Check Point hardware deal standard | Hardware-heavy deal margin
Displaced 29100/29200 units |  | units |  |  | Upgrades that displace a box sale
Forgone box gross profit |  | $ |  |  | Box GP we would have earned on those units
Module GP already counted |  | $ |  |  | Module GP from the same customers (already in the base)
Net cannibalization impact |  | $ |  |  | Negative = net GP forgone vs. the box counterfactual
Memo · net contribution before cannibalization (gross) |  | $ |  |  | Reference: the pre-haircut figure the deck used to show
Memo · ROI before cannibalization (gross) |  |  |  | Adjusted net ÷ investment | Reference only; the headline ROI above is net of cannibalization
Check Point Software Technologies · Confidential ¦ Barak Rozenfeld · Senior PM Assignment 2026 ¦ Slide 16 ¦ Cream = editable input · grey = formula (recalculates).

## 12 · Alternatives
Slide 12 — Four alternatives for accelerating TP under TLS
Each alternative has its own sheet with a bottom-up breakdown of how the time and cost were derived. Criterion: throughput per RU without sacrificing flexibility.
# | Alternative | What we develop | Dev time | Dev cost (NRE) | Throughput (today 10) & verdict
1 | Build our own ASIC | Our own dedicated chip | 3–5 years | $300M+ | ~40+ · Rejected — cost & time prohibitive, inflexible
2 | Self-designed FPGA | FPGA designed by Check Point | ~3 years | $30–50M | ~30–40 · Rejected — costly, HDL per engine
3 | Use a ConnectX-7 SmartNIC | Off-the-shelf NVIDIA ConnectX-7 | ~12 months | ~$3M | 10→~20 (×2) · Rejected — crypto only, no Arm cores
✓ | Use a BlueField-3 card (CHOSEN) | Existing NVIDIA BlueField-3 card | ~18 months | ~$7M | 10→~40 (×4) · CHOSEN — best TP/RU + software-updatable
Basis: ASIC/FPGA are industry precedent (IBS/McKinsey); ConnectX & BlueField-3 are our bottom-up estimate. Throughput for ASIC/FPGA is a qualitative comparison.

## Alt 1 — Own ASIC
Alternative 1 — Build our own ASIC
A Check Point-designed dedicated chip. Rejected: cost and time are prohibitive and the logic is burned into silicon — a new engine means a whole new hardware generation.
Headline
Metric | Value | Basis
Development time | 3–5 years | Tape-out (~2 yr) + bring-up + software; industry precedent
Development cost (NRE) | $300M+ | 7nm full design cost (IBS / McKinsey chip-design cost by node)
Throughput (TP+TLS/RU) | ~40+ | Reaches the target; x86 policy stage then the limit (qualitative)
Verdict | Rejected | Highest cost, longest time, zero flexibility for new engines / AI-ML
How the development TIME was derived
Phase | Duration | Why this long
Architecture + RTL design | ~12 months | Specify the crypto + inspection pipelines and write the RTL
Verification & validation | ~12 months | Exhaustive sim/formal; a silicon bug after tape-out is catastrophic
Physical design + 7nm tape-out | ~6–12 months | Place-and-route, mask set, fab; ~2 yr cumulative to first silicon
Fab + first silicon + bring-up | ~6 months | Wafer run, packaging, lab bring-up
Respin (typical) + re-validation | ~6–12 months | First silicon rarely ships; budget at least one respin
Firmware + Gaia/platform integration | ~6–12 months | Drivers and software stack, overlaps bring-up
Calendar total (with overlap) | 3–5 years | Industry precedent for a new security ASIC
How the development COST (NRE) was derived
Component | Amount | Note / assumption
IP licensing + architecture + RTL | 55000000 | Licensed crypto/networking IP + design team
Verification & validation | 60000000 | Largest single line in modern SoC design
Physical design + 7nm mask set | 45000000 | Masks alone ~$15–25M at 7nm, plus place-and-route
Prototyping, bring-up, 1 respin | 40000000 | Each respin ~$5–15M in masks + lost time
Firmware + software + drivers | 45000000 | Full stack to run on the new silicon
Qualification, FIPS/EAL, PM, overhead | 55000000 | Certification + multi-year program overhead
Total NRE (≈ IBS/McKinsey 7nm) |  | Sums to ~$300M; '+': extra respins push well beyond

## Alt 2 — FPGA
Alternative 2 — Self-designed FPGA
An FPGA designed by Check Point. Rejected: still costly, every new engine needs fresh HDL work, and performance trails a custom ASIC. The $30–50M range below is built bottom-up to a ~$40M midpoint.
Headline
Metric | Value | Basis
Development time | ~3 years | HDL + timing closure; no tape-out, so shorter than an ASIC
Development cost (NRE) | $30–50M | Bottom-up ~$40M; range driven by team size & board respins
Throughput (TP+TLS/RU) | ~30–40 | Frequency / logic-density gap versus a custom ASIC (qualitative)
Verdict | Rejected | Costly, HDL effort per new engine, slower than an ASIC
How the development TIME was derived
Phase | Duration | Why this long
Architecture + HDL design | ~12–15 months | RTL for the crypto + inspection pipelines
Verification + timing closure | ~9–12 months | Timing closure on advanced FPGAs is the long pole
Board/card design + bring-up | ~6–9 months | Overlaps HDL; custom card around the FPGA
Firmware/driver + integration | ~6 months | Into Gaia / the 9000 platform
Qualification / certification | ~6 months | FIPS / EAL on the new card
Calendar total (with overlap) | ~3 years | No tape-out, so ~1–2 yr shorter than an ASIC
How the development COST (NRE) was derived
Component | Amount | Note / assumption
FTE — HDL/verif/firmware/board team | 25 | Specialist HDL engineers are scarce & expensive
Years | 3 | Matches the ~3-year timeline above
Loaded cost per FTE-year | 280000 | Fully loaded (salary + overhead + tools share)
Engineering team
EDA + FPGA tool licenses (3 yr) | 4000000 | Synopsys/Cadence/FPGA vendor toolchains
Board design + 3 respins + prototypes | 6000000 | Main swing factor for the $30–50M range
Premium FPGA silicon (dev + qual lots) | 3000000 | High-end Versal/Agilex-class parts
Qualification & certification (FIPS/EAL) | 3000000 | Regulated-market certification
Program mgmt + contingency | 3000000 | PM, risk buffer
Total NRE (midpoint of $30–50M) |  | ≈$40M; 20 FTE & fewer respins → ~$30M, 30 FTE & more → ~$50M

## Alt 3 — ConnectX NIC
Alternative 3 — Use a ConnectX-7 SmartNIC
An off-the-shelf NVIDIA ConnectX-7 NIC. Rejected: fixed-function offload (inline TLS/IPsec crypto only) with no programmable Arm cores, so it cannot run IPS or an AI/ML engine on-card.
Headline
Metric | Value | Basis
Development time | ~12 months | Driver + crypto-offload integration on an off-the-shelf NIC
Development cost (NRE) | ~$3M | Bottom-up; cheapest option but limited capability
Throughput (TP+TLS/RU) | 10 → ~20 (×2) | TLS crypto offload only; IPS still runs on the x86
Verdict | Rejected | Relieves only TLS crypto; the x86 stays the inspection bottleneck
How the development TIME was derived
Phase | Duration | Why this long
Driver bring-up in Gaia | ~6 months | Standard NIC driver model; no on-card OS to build
TLS/IPsec crypto-offload integration | ~6 months | Wire inline crypto offload into the data path (overlaps driver)
Calendar total (with overlap) | ~12 months | Off-the-shelf NIC, no DPU software stack to build
How the development COST (NRE) was derived
Component | Amount | Note / assumption
FTE — integration team | 6 | Small team; no on-card software platform
Years | 1 | Matches the ~12-month timeline
Loaded cost per FTE-year | 250000 | Fully loaded
Engineering team
ConnectX-7 dev cards + lab setup | 300000 | Off-the-shelf hardware
Test tooling | 200000 | Traffic generators, test rigs
Qualification (no new silicon) | 500000 | Lighter — reusing a shipping NIC
Contingency | 500000 | Risk buffer
Total NRE |  | Sums to ~$3M

## Alt 4 — BlueField-3 (chosen)
Alternative 4 — Use a BlueField-3 acceleration card ✓ CHOSEN
An existing NVIDIA BlueField-3 card in a Check Point-format slot. Chosen: best throughput per RU without sacrificing flexibility — a new engine (incl. AI/ML) ships as a software update, and BF-3 is already proven in Check Point AI Cloud Protect (AIFF). Cream = editable input · grey = formula.
Headline
Metric | Value | Basis
Development time | ~18 months | ~12 mo integration + ~6 mo PoC on an existing BF-3
Development cost (NRE) | ~$7M | Bottom-up: team + dev kits + tooling + cert + contingency
Throughput (TP+TLS/RU) | 10 → ~40 (×4) | Offloads TLS crypto + IPS; PoC gate is a conservative 25G+ (×2.5)
Verdict | CHOSEN | Best TP/RU, software-updatable, vendor + platform already proven
How the development TIME was derived
Phase | Duration | Why this long
Integration | 12 months | Card in the I/O slot, drivers, TLS+IPS offload pipeline in Gaia
PoC | 6 months | Validate 25G+ gate, power / thermal / mechanical fit in the card format
Calendar total | 18 months | Not from scratch — the 9000 already runs acceleration cards; BF-3 is in AIFF
How the development COST (NRE) was derived
Component | Amount | Note / assumption
Engineers | 12 | Core R&D team for integration + PoC
Duration (months) | 18 | Integration + PoC window
Loaded cost per engineer-month | 20833 | ≈ $250K / engineer-year, fully loaded
R&D team
BlueField-3 dev kits | 800000 | NVIDIA BF-3 development hardware
Lab + test tooling | 600000 | Traffic generators, test rigs, bench
FIPS / certification pre-work | 600000 | Early cert groundwork during the PoC
Contingency | 500000 | Risk buffer for the PoC phase
Total NRE |  | Sums to ~$7.0M. The full program on '2 · Investment' is $7.2M (adds HW/FIPS + GTM beyond this R&D+PoC core)

## PoC — detail
PoC — detailed plan (investment structure + effort timeline)
The $2.9M / ~6-month Proof-of-Concept that must clear ONE gate (25 Gbps+ under TLS) before the $4.3M GA spend is released. Cream = editable input · grey = formula (recalculates).
Headline
Metric | Value | Basis
Success gate | 25 Gbps+ under TLS (×2.5) | Primary exit criterion vs 10G under TP+TLS today
Duration | ~6 months | Effort estimate, not a schedule commitment
PoC cost |  | Bottom-up total of the investment structure below
Team | 10 engineers | Focused subset on the offload boundary
Held back to GA | $4.3M | Released only if the gate is met — otherwise we stop
Investment structure · PoC — bottom-up to $2.9M
R&D build-up
Engineers (PoC) | 10 |  |  | Focused subset — core offload + driver + perf
Duration | 6 | months |  | To the 25 Gbps+ gate
Loaded cost / engineer-month | 20833
R&D subtotal = engineers × months × rate |  |  |  | ≈ $1.25M
Line item (dev kits / HW / GTM) | Qty | Unit cost | Amount | Note
BF-3 dev boards | 6 | 15000 |  | Dev/test units for the PoC team
DOCA SDK / support | 1 | 120000 |  | SDK, licenses and developer support
NVIDIA NRE (PoC portion) | 1 | 330000 |  | Non-recurring integration engineering
Lab / TLS test harness | 1 | 110000 |  | Traffic generators + TLS test rig
Early thermal / airflow simulation | 1 | 300000 |  | 1RU airflow for ~75W added
PSU / signal-integrity pre-check | 1 | 150000 |  | Electrical headroom validation
FIPS 140-3 scoping | 1 | 150000 |  | Early cert groundwork (BF-3 module already approved)
Design-partner program prep | 1 | 250000 |  | Line up beta partners before GA
PoC engineering support | 1 | 150000 |  | Field / SE support during the PoC
Non-R&D subtotal |  |  |  | dev kits/NRE $0.65M + HW/thermal/FIPS $0.6M + GTM $0.4M
TOTAL PoC = R&D + non-R&D |  |  |  | ≈ $2.9M (phase-slice of the $7.2M full program)
Effort timeline · PoC — phases sum to ~6 months
Phase | Months |  | What happens / output
Dev-kit & lab bring-up | 1 |  | Set up BF-3 boards, lab and baseline — environment ready
Offload integration (core) | 2 |  | DOCA/Gaia driver + CoreXL offload path — TLS path running on the card
TLS gate measurement (25G+) | 2 |  | Measure TP under TLS and tune — the make-or-break gate
Thermal + FIPS scoping | 1 |  | 1RU thermal sim + FIPS path — headroom & cert path confirmed
Total |  |  | ≈ 6 months to the gate
Success gate & exit criteria
Primary gate | ≥ 25 Gbps TP under TLS (×2.5 vs 10G today) — the go/no-go number
Secondary | ~85% of IPS signatures compile on the RXP engine
Thermal / power | ~75W added fits within 1RU PSU & airflow headroom
Certification | FIPS 140-3 path confirmed — BF-3 crypto module already approved
Exit rule | If the primary gate is missed → stop before the $4.3M GA spend